Falcon Product Plan

0.2

Revision History

| Version | Date | Author | Comments |
| --- | --- | --- | --- |
| 0.1 | 9/4/92 | PatrickA | first draft |
| 0.2 | 12/8/92 | Patricka | added Win16 client. Modem target chaged from 200 to 101. Schedule adjusted for new NT release dates, IHV update included. |

# Introduction

The purpose of this document is to identify all components that need to be delivered for a successful release of Falcon. This document also details the major milestones that must be met by the various Microsoft departments and IHVs working on this project to ensure a successful rollout of Falcon.

This document is intended to help RAS team members keep track of where we are.  It will be updated periodically to reflect the state of the RAS project.

# Engineering

## Engineering Deliverables

NT RAS Client software

NT RAS 1 port Server software

NT RAS 32 port Server software

Snowball client (win16)

## Milestones

| Milestone | Sceduled | Current | Comments |
| --- | --- | --- | --- |
| Functional Spec Complete | 6/92 | DONE |  |
| Point-to-point Connection over null modem | 8/20/92 | DONE |  |
| Multiple dynamic point-to-point connections | 9/10/92 | DONE |  |
| NetBIOS Gateway Functional | 10/20/92 | DONE |  |
| Complete RAS connection using Win/NT UI | 10/26/92 | DONE |  |
| Code Complete | 10/30/92 | DONE |  |
| System Test Entry | 11/1/92 | 11/1/92 |  |
| Internal Beta | 12/1/92 | 12/15/92 | moved to 12/15 due to RAS integration problems and unavailablility of suitable NT build. Will go internal beta on NT build 349. |
| Beta I | 1/4/93 | 1/29/93 | merged with NT beta II |
| Beta II | N/A | 3/17/93 | win 16 client added |
| Golden Master | 3/1/93 | 5/17/93 | within 30 days of NT ship |
| OEM Adaptation Kit . Source OAK is our complete build environment,source, tools and test/tools documentation on a tape. ODK (OEM Distribution Kit) is the golden master disks and postscript docs. | 3/15/93 | 6/15/93 |  |

# System test

## Deliverables

System Test Plan

System Test entry criteria

Network Interoperability Testing

LAN Manager, Sparta, Windows NT, Pathworks, LAN Server, 3+Open.

Application Testing

MS Mail 3.0, Schedule+, Lotus Notes, Ocean Isle Reach Out, pcAnyWhere ... other applications.

48 Hr Maximum Load Stress Test

## Milestones

| Milestone | Scheduled | Current | Comments |
| --- | --- | --- | --- |
| Complete System Test Plan including ST entry criteria |  | DONE |  |
| System Test Entry | 11/15/92 | 11/15/92 |  |
| Internal Beta | 12/1/92 | 12/7/92 |  |
| Beta I | 1/4/93 | 1/29/93 | merged with NT beta II |
| Beta II | N/A | 3/17/93 | win 16 client added |
| Golden Master | 3/1/93 | 5/31/93 | within 30 days of NT ship |
| OEM Adaptation Kit . Source OAK is our complete build environment,source, tools and test/tools documentation on a tape. ODK (OEM Distribution Kit) is the golden master disks and postscript docs. | 3/15/93 | 6/15/93 |  |

# User Ed

## Deliverables

On-Line Help for Windows NT and Windows for Workgroups

·	On-Line help for RAS Phone Book.

·	On-Line help RAS Admin

·	On-Line help for RASDIAL (command line)

Quick User Reference

·	Window NT 3.1

·	Windows for Workgroups 3.2

·	Windows for Workgroups 3.1 and LAN Manager clients

Administrators Guide

·	Windows NT 1 Port RAS server

·	Windows NT multiport RAS server

Release Notes

## Milestones

| Milestone | Scheduled | Current | Comments |
| --- | --- | --- | --- |
| Complete Admin Manual | 10/30/92 | Done |  |
| Complete On-Line Help | 10/30/92 | 1/20/93 | Plan revised for external beta rather than internal beta. |
| First Technical Review (Admin Guide, Quick Reference Card, On-Line help) | 11/6/92 | DONE | 1st technical review covered admin guide. QRC and On-line help pending |
| Revise Manual | 11/24/92 | DONE |  |
| Integrate with RASPHONE, RASADMIN, and RASDIAL | 11/24/92 | 1/22/93 | Milestone has been changed from revision and integration, to integration only. |
| Second Technical review (Admin Guide, Quick Reference Card) | 12/4/92 | 2/4/93 | Written review from developers. One on one reviews with individual developers. Group review for 1st technical review was not efficient. |
| Second Technical review (On-Line Help) | 12/18/92 | 2/4/93 | Converged with admin and user guide reviews. |
| Final Edit | 12/18/92 | 2/26/93 |  |
| Hand off of manuals to IPG | 1/4/93 | 3/12/93 | ITG will actually start generating glossary of key terms to be localized on 2/4/93. However, stable doc for translation is on 3/12/93 |
| To Print | 1/18/93 | 3/26/93 |  |
| Hand off final On-Line documentation to IPG | 2/15/93 | 4/12/93 | CurtJo will get contact directly from DustanJ and will point contact in Ireland to documentation sources on the net. |
| Complete Release Notes | 2/22/93 | 5/16/93 | readme file lives till the last day. |
| Golden Master | 3/1/93 | 5/17/93 | within 30 days of NT ship |
| OEM Adaptation Kit . Source OAK is our complete build environment,source, tools and test/tools documentation on a tape. ODK (OEM Distribution Kit) is the golden master disks and postscript docs. | 3/15/93 | 6/15/93 |  |

# Localization

## Deliverables

Translate Falcon to the following languages

·	French

·	German

IPG's focus will be French and German.  English, French and German cover 90% of our market.  There are currently no plans for RAS group to implement or test Swedish and Italian releases.  Ireland may produce Swedish and Italian releases, but this is not very clear to me at this time.  I am not tracking Swedish and Italian releases.

## Mile Stones (French and German)

| Milestone | Scheduled | Current | Comments |
| --- | --- | --- | --- |
| Start translation of manuals | 1/4/93 | 3/12/93 | Moved to synch NT RAS up with NT after discussion with DustanJ |
| Documentation manuals translation complete | 1/24/93 | 4/12/93 |  |
| Start translation of On-Line help | 2/15/93 | 4/12/93 |  |
| Film to Ireland | 3/7/93 | 4/30/93 |  |
| French, German RC1. (Start final regression testing) | 4/6/93 | 5/17/93 |  |
| On-Line documentation hand off to Ireland (manufacturing) | 4/20/93 | ? | Need details from DustanJ |
| Code hand off to Ireland.*manufacturing) | 4/20/93 | ? | Need details from DustanJ |
| First Customer Ship | 4/30/93 | within 30 days of 5/17/93 |  |

# Marketing

## Deliverables

Packaging Plan

Build of Materials

Product Collateral

Product Roll Out (press release, OEM agreements, etc)

## Milestones

| Milestone | Scheduled | Current | Comments |
| --- | --- | --- | --- |
| Packaging plan complete (SKUs identified) | 8/13/92 | 12/15/92 | Packaging is being reconsidered by CNS marketing. Currently have two products: (1) NT RAS Desktop, (2) NT RAS server. Possibility of bundling RAS client software with NT and RAS 1 port server with NT advanaced server |
| Technical review of marketing collateral | 1/15/93 | 1/15/93 |  |
| Collateral complete | 3/1/93 | 3/1/93 |  |
| Get OEM agreements in place. |  |  |  |
| Product roll out | 3/15/93 (pending NT release) | 3/15/93 |  |
| OEM Adaptation Kit . Source OAK is our complete build environment,source, tools and test/tools documentation on a tape. ODK (OEM Distribution Kit) is the golden master disks and postscript docs. | 3/15/93 | 6/15/93 |  |

note:  marketing roll out plan and collateral will be merged with NT marketing effort.  These numbers are estimates of when RAS portions will be ready to go.

# Eicon

## Deliverables

Eicon ECXPAD.SYS for Windows NT.

## Milestones

| Milestone | Scheduled | Current | Comments |
| --- | --- | --- | --- |
| Software to Microsoft | 1/4/93 | 12/24/92 | Alpha level driver. Will deliver beta code on 1/27/93. |
| Beta I | 1/4/93 | 1/29/93 | merged with NT beta II |
| Beta II | N/A | 3/17/93 | win 16 client added |
| Golden Master | 3/1/93 | 5/31/93 | within 30 days of NT ship |

## Making it happen

1.	Ship RAS 1.1 DONE

2.	Get initial NT schedules from Eicon. DONE

3.	Arrange date for exchange of Software between MS and Eicon.  We send alpha code complete integrated product to Eicon, they send us alpha driver.  DONE

4.	Establish one connection via Eicon adapter.

5.	Establish multiple connection milestone.

6.	Arrange date for setup complete prior to MS internal beta.

7.	Setup Remote Access sharepoint for updating software to each other.  RAS on NT  becomes self hosted.  Remote access will be done via Falcon.

# Atlantis

## Deliverables

ATLCOM for Windows NT

## Milestones

| Milestone | Scheduled | Current | Comments |
| --- | --- | --- | --- |
| Software to Microsoft | 1/4/93 |  |  |
| Beta I | 1/4/93 | 1/29/93 | not confirmed |
| Beta II | N/A | 3/17/93 | not confirmed |
| Golden Master | 3/1/93 | 5/31/93 | not confirmed |

These are all as yet unconfirmed with Atlantis.  Atlantis has nto responded to my e-mail messages in a concrete manner.  The only information we have at this time is "The NT developments are on schedule, the first integration tests will begin the 2nd week of January."  This is obviously not enough information for us to feel secure with Atlantis. Will conitnue to track as best as I can.

## Making it happen

1.	Ship RAS 1.1 DONE

2.	Get initial NT schedules from Atlantis. DONE

3.	Arrange date for exchange of Software between MS and Atlantis.  We send alpha code complete integrated product to Atlantis, they send us alpha driver.

4.	Establish one connection via Atlantis adapter.

5.	Establish multiple connection milestone.

6.	Arrange date for setup complete prior to MS internale beta.

7.	Setup Remote Access sharepoint for updating software to each other.  RAS on NT  becomes self hosted.  Remote access will be done via Falcon.

# Quadron Corp

## Deliverables

NT serial driver for IBM Artic cards

## Milestones

| Milestone | Scheduled | Current | Comments |
| --- | --- | --- | --- |
| Software to Microsoft | 1/4/93 | ? | Need to get date out of Quadron for this |
| Beta I | 1/4/93 | 1/29/93 | merged with NT beta II |
| Beta II | N/A | 3/17/93 | win 16 client added |
| Golden Master | 3/1/93 | 5/31/93 | within 30 days of NT ship |

## Making it Happen

1.	Understand work needed.  Since it's an intelligent adapter, will firmware need to be developed in addition to a host driver?  Will only a host driver be needed?  Setup program?  What support will IBM provide?  Does IBM have firmware in place?

DONE

2.	Get cards and documentation from IBM.  Go through material with Jawad and come up with estimate of work required. Get second opinion from TonyE.

IBM promised to send, but did not follow through.  I am dropping this.  Quadron has come on board the NT train.  No need to follow up with contractors.

3.	Find out exactly how many Quadron drivers were shipped.  Why weren't more drivers shipped?  How do we think this problem will go away on the NT platform? What's the installed base of IBM Artic cards?Need this information before meeting with Quadron.  try to get Quadron to come up here.

MS Library was unable to find installed base figures for IBM ARTIC.  MS SEs indicate that ARTIC is in only 20-30% of current RAS installations, but large base of ARTIC cards in big blue installations.  Need to support it for insurance.

5.	Get Quadron excited about NT RAS.

DONE.

6.	Consider getting third party contractor working on this.

DONE.  Discussed contract with ARTEC Technologies.  Dropped negotiations because we cannot justify MS spending 50-70K for this driver.  Pursued Quadron instead.

7.	Establish e-mail communication with all Quadron parties.

8.	Arrange date for exchange of Software between MS and Quadron.  We send alpha code complete integrated product to Quadron, they send us alpha driver.

9.	Establish one connection via IBM Artic adapter.

10.	Establish multiple connection milestone.

11.	Arrange date for setup complete prior to MS internal beta.

12.	Setup Remote Access sharepoint for updating software to each other.   RAS on NT  becomes self hosted.  Remote access will be done via Falcon.

# Digiboard

## Deliverables

NT serial driver for Digiboard Adapter

## Milestones

| Milestone | Scheduled | Current | Comments |
| --- | --- | --- | --- |
| Code Complete CX ISA system | 11/30/92 | DONE | Digiboard came in house to get their driver debugged. They have delivered an alpha driver to us for initial ST |
| System Test Entry | 1/4/93 |  |  |
| Microsoft and Digiboard self hosted with RAS and CX system on NT. Exchange binaries between sites via RAS on NT | 12/1/92 | 1/29/93 | moved to coincide with NT beta II. Need to synch up on NT build for self host. |
| Beta I (PC/8i, PC/8e, MC/8i, CX system adapters) | 1/4/93 | 1/29/93 | merged with NT beta II |
| Beta II | N/A | 3/17/93 | win 16 client added |
| Golden Master | 3/1/93 | 5/31/93 | within 30 days of NT ship |

## Making it happen

1.	Get initial schedules from Digiboard.

DONE

2.	Get NT Serial Driver component tests to Digiboard

DONE.  Requested to have these tests included in NT DDK for other vendors also.

3.	Plan to visit Digiboard next month to see where they are.  Set up meeting to discuss possible OEM deal, ISDN work, and talk with developers about where they are.

Digiboard came to visit us twice instead.  They're really psyched up!

4.	Establish e-mail communication with all Digiboard parties (John Gaylord, Dror Kessler dror@digibd.com, Rick Logan rik@digibd.com)

DONE

5.	Arrange date for exchange of Software between MS and Digiboard.  We send alpha code complete integrated product to Digiboard, they send us alpha driver.

DONE

6.	Establish one connection via digiboard adapter.

7.	Establish multiple connection milestone.

8.	Arrange date for setup complete prior to MS internale beta.

9.	Setup Remote Access sharepoint for updating software to each other. RAS on NT  becomes self hosted.  Remote access will be done via Falcon.

# Program Management

## Deliverables

Setup Functional Spec

Modem information for 101 modem models shipped in the United States.

Modem information for 100 modems shipped in Europe, Asia-Pacific, Latin America and Australia

Product evangilization

·	SEs informed about Falcon

·	MCS informed about Falcon

·	Networld (will Falcon be demoable in October?)

Hardware drivers for Async and X.25 cards:

·	Eicon

·	Atlantis

·	Digiboard

·	IBM Artic

Ship high quality product

## Milestones

| Milestone | Last Date | Current Date | Comments |
| --- | --- | --- | --- |
| Setup functional spec complete | 6/92 | 9/24/92 |  |
| Beta Plan review | 9/27/92 | done |  |
| Beta Plan complete | 9/31/92 | 12/31/92 | Will add specific areas that I need tested by individual beta sites. |
| Get all RAS IHVs up and running with NT DDK | 9/27/92 | done | IHVs remain a risk but we are managing them as well as we can |
| Get commitment from all RAS IHVs to line up with Falcon schedules | 10/15/92 | Done (Digiboard, Eicon, Comptrol, Quadron) Not done(Atlantis) |  |
| Complete US modem research | 11//30/92 | done |  |
| Internal Beta | 12/1/92 | delayed to 12/15/92. Intagration problems, also waiting for NT build that meets our needs. |  |
| Beta I | 1/4/93 | 1/29/93 | synch with NT beta 2 |
| Complete international modem research | 2/26/93 | ? |  |
| Product Release | 3/1/93 | 5/17/93 | NT golden plus 30 days |
| OEM Adaptation Kit . Source OAK is our complete build environment,source, tools and test/tools documentation on a tape. ODK (OEM Distribution Kit) is the golden master disks and postscript docs. | 3/15/93 | 6/15/93 |  |

## Making it happen

1.	Target top 20 modem vendors and get modems supported from each of these.

DONE

2.	Get contractor in house to call up modem vendors and write up strings for each modem that comes in.  Follow up on lead given by GertG and see if we can get a contractor that way. contact Data Storm (ProCom Plus) to see if they are open to working with us.

DONE

3.	Get at least one wireless modem supported.  Talk to Motorolla

4.	Understand modem technologies completely (MNP5, V.42bis etc.)

5.	Understand pricing model for wireless modems.  When are they cost effective as compared with existing modems?

6.	Understand wireless modem technoloy.  Range, interoperablity with existing modems, industry standards.

7.	Leverage off of work done by mail group where possible, especially with regard to European modems.