# Cairo Disk Administrator Development Plan

Bruce Forstall

Last saved:

Printed: 10/11/1994 02:10:00 PM

Updated 10/11/94.

This note summarizes and re-evaluates my perspective of the development work items that need to be performed for the Cairo Disk Administrator (windisk), with comments on the schedule for getting them done. Beware: I’ve tried to be pretty detailed about the work items. Also, not all of these are committed to the Cairo product.

KevinSch has written a document titled “Windisk 2.0” (filename windisk.doc) that is mostly a UI specification. I don’t know where this document lives.

The windisk extension interface, as it exists today, is found in the windisk project “types” subdirectory. Currently:  \\savik\win40\src\sysmgmt\windisk\types\*.idl.

Table of Contents

Cairo Disk Administrator Development Plan

Introduction

The Work Items: Must

Chkdsk

Format and Chkdsk

DoubleSpace support.

Hot plugging support

Implement “last chkdsk”

File system conversion

Remote windisk

New Menu UI

New Create Volume UI

The Work Items: Should

Better DoubleSpace UI

Miscellaneous UI enhancements

New commands for mirrored sets

Volumes view changes: should

Format

The Work Items: Would Be Nice

Controller/disk view

Advanced FT support

FTAPI support

Multilevel FT support

OLE Automation

Miscellaneous: Would Be Nice

Volumes view changes: would be nice

Pagefile support

The Work Items: Won’t do

Boot sector configuration

Volume creation wizard

Minimize disk bars in disks view

FAT partition shrinking

Concurrent format/chkdsk

# Introduction

The Disk Administrator (windisk) started as a hard disk repartitioning tool to replace DOS FDISK, with some additional capabilities to support configuring NT storage fault tolerance. In the work items listed below, you’ll notice that it has been evolving in the minds of program management and developers to include more and more volume-related operations, such as format and chkdsk. It has been suggested that windisk should become the complete storage subsystem configuration tool for NT, providing configuration and information display for storage system components including disk controllers and busses (e.g., SCSI), to integrated hardware and software RAID configuration, to high-level volume configuration.

This document describes what will appear in windisk, from the development perspective.

The items are arranged approximately in priority order, and are given a priority of ‘must’, ‘should’, ‘would be nice’, and ‘no’, or ‘won’t do’. However, due to dependencies, the items might not be performed in the order given.

Each item includes a description of:

- what it is, including any relevant information that indicates its complexity,

- the time I expect it will take to complete,

- a description of its dependencies, and

- its risk factor: doable or not.

# The Work Items: Must

## Chkdsk

Chkdsk messages need to be massaged in several ways:

- Any message that has the literal text “CHKDSK” needs to either be changed in ulib.dll to be independent of the client (i.e., so it works for both chkdsk.exe and windisk), or we need to map the message within windisk to be something reasonable. The former is preferable. What the latter entails is matching a message number, and mapping it to another message number for windisk use. Note that we don’t search for text strings and cut-and-paste based on that. Preferably, both messages will reside in ulib.dll, and hence be centralized. A question remains: how much do we need to worry about preserving the exact output text of the utilities?  A possible design: a “GUI bit” and a “character bit” in the message file. The utilities spit out all potential messages. The GUI discards all that don’t have the “GUI bit” set, and the character-mode front-end discards those without the character-bit set. Note that a message may have both set.

- Any queries posed by the tools need to be answered by windisk intelligently. For example, attempting a chkdsk on the NT system volume returns the query, “Do you want AUTOCHK to be run the next time that the machine reboots? [Y]”. For this, we may need a dialog box to perform the query. This is implemented as follows. The caller of the utilities DLL provides an implementation of the MESSAGE feedback class. The IsYesResponse() member takes input.

- We may want to take progress messages such as “X percent completed.” and remove them from the set of messages that we show the user at the end of chkdsk. Similarly for the message “Warning! F parameters not specified. Running CHKDSK in read-only mode.”

Priority: must. Time: 1 week to figure it out; 2 1/2 weeks to implement it. Risk: medium.

RobDu has emphasized to me many times how complicated the OFS chkdsk code is, and how it would be difficult to impossible to come up with a reasonable single “% done” figure as a progress message. Since I’m not familiar with the CHKDSK code for the other file systems (and haven’t received any responses from people who are), I can’t make an estimate on their difficulty. Presumably FAT is fairly straightforward. NTFS already has multi-pass %done numbers. HPFS is presumably something between FAT and OFS.

We have discussed various progress indication metrics that might work for OFS. Some ideas:

- A % done calculated as the ratio of the current pass divided by the current thinking as to the maximum number of passes. The problem is that the number of passes is not known a priori. If we start with a pessimistic maximum and shrink this number as we gain knowledge, we at least get a monotonically increasing %done number. However, each pass might take vastly different amounts of time, so the %done certainly doesn’t reflect time.

- Simply a flashing “Working...” indicator (that I have now), that is coupled to actual progress as follows. The back-end spits out “I’m still alive and working” messages. If I see one within any X second period (where X probably = 0.7), then I flash the indicator. Otherwise, I don’t.

Quiting OFS chkdsk in the middle of operation may be dangerous. Right now, due to the messages (or lack thereof), it is impossible to cause chkdsk to exit cleanly. Assuming we added appropriate progress messages to allow us to have a place to put “please exit now” code, it might be bad to exit at some points. For instance, the chkdsk code might not be written to exit cleanly (releasing resources, etc) from arbitrary locations where progress messages would be inserted. In addition, in Fix mode, the written fixes might not be transacted, such that quitting at an arbitrary point would leave the volume in a worse state than before. It might be possible to quit at any time, if: (1) you are in verify mode, or (2) you are in Fix mode, but no errors have been encountered.

## Format and Chkdsk

- By KevinSch’s prototype, we must handle “stop” during a format or chkdsk. It turns out that if a full (not quick) format is stopped before the 100% mark is met, no change has actually been made to the data on the volume, and hence the volume is completely intact. Only after the 100% mark is hit does any real formatting happen. Currently there is no way to stop chkdsk: since there are no progress messages, my code never gets control, and hence never gets the chance to force a quit. In the NTFS case, where there is feedback, I don’t believe chkdsk even cares about FALSE (“please quit now”) returns. Assuming we get control, and can detect a user desire to exit, we must pause the work thread, waiting for a synchronization event from the UI thread to continue. Possible synchronization: use a global variable and spin wait in the worker thread.

Priority: must. Time: 2 days. Risk: low.

## Use Cairo SDK object definition tools

Convert extension interfaces to Cairo IDL format. The interface definitions are currently specified as C++ types and classes. They should be specified using the standard Cairo SDK interface and class specification tools. The problem with this currently is that I have function pointers in the interface, and this is unsupported by the SDK tools.

Priority: must. Time: 1 week. Risk: high.

## DoubleSpace support.

If DoubleSpace gets on the schedule for a future NT release, the DoubleSpace support that Bob added (and I merged) for Daytona windisk must be re-enabled, tested, etc. Or, it should be re-examined.

Priority: must. Time: 1 week. Risk: low.

## Hot plugging support

Support dynamically adding and removing disks.

Windisk has to provide one function:

- Prepare drive for removal. This means explicitly dismount each volume on the drive, locking the drive and indicating to user when this is done. If a volume can’t be locked, we could warn the user. The dismount command should cause caches to be flushed and references forced shut.

Priority: would be nice. Time: 1 week. Risk: high: dependent on low-level support.

## Implement “last chkdsk”

This comes from the Chicago design. We could implement “last chkdsk” (and perhaps the date/time when the volume was formatted?), as the chkdsk operation is guaranteed to be supported by all file systems. This requires: (1) picking someplace in the registry to save the last chkdsk time for each volume, (2) modifying chkdsk.exe to set this time when a “chkdsk /f” is run, (3) modifying windisk to modify this time, (4) modifying format to clear this time when a volume is formatted, (5) modifying windisk to clear/copy the time when a volume changes drive letter. (i.e., the time for the old drive letter gets cleared, the new drive letter time gets the value the old drive letter had---a copy)
One problem here is the current placement of chkdsk in extension code. Windisk has no idea that chkdsk is a supported operation; it only knows that the file system provides certain interesting operations. We might have to “pull” chkdsk up and make it a required operation, in the extension interface.

There is some code in the “unused” subdirectory for this.

Priority: must. Time: 1 1/2 weeks. Risk: low.

## File system conversion

Support invoking all the file system converters from windisk. NT currently ships FAT to NTFS and HPFS to NTFS conversions. OFS will support direct FAT to OFS and NTFS to OFS conversion, but will require HPFS to first be converted to NTFS before being converted to OFS.

The conversion functions exist in the utilities DLLs (u*.dll).

Add a “Convert” menu item to the “Tools” menu, and on any context menu if it is legal. It is legal for single volume selections of file systems that can be converted, which is all but OFS. A dialog box would show the target file system, which you could choose from a combo box. The proper u*.dll would be used based on the target file system.

Priority: must. Time: 1 week. Risk: medium.

## Remote windisk

Invoke windisk on a remote machine. The basic problem is that you cannot call Win32 APIs remotely. So, we must break windisk into a client portion which performs UI to the user, and a server portion which runs on the machine of interest and performs no UI. The communication is via CairOLE interfaces.

A remote session is starts by running the client which invokes the server and starts up the communication. CoGetClassObject() will support starting up a server at an arbitrary remote location; the pvReserved parameter will specify the activation location. Also, EricB & AnirudhS will provide a “systems management helper object” that some control panel applets use for remote help. I will piggyback on this. This will be a “junk object” supporting many seemingly random interfaces and APIs necessary to achieve remote systems mgmt operations.

It has been suggested that the best way to approach this is to complete enough other items on this work item list such that we would feel comfortable shipping windisk. Take a snapshot. Then, start hacking away and see what happens. It is likely only through programming that we will find the real problems.

Priority: should. Time: 2-3 months, minimum. Risk: high.

## New Menu UI

KevinSch has designed a new UI for the menu items in windisk. Basically, instead of having Partition and Fault Tolerance menu bar items, we will only have a single Volume item, that selectively includes all the possible menu items from before. That is, instead of simply concatenating the menus, which would make the new “Volume” menu unwieldy, we only include on the menu those items which are allowable based on the current selection. This works because a large number of the options are mutually exclusive. Thus, the menu bar would have almost the same items that the context menu currently has.

This introduces a weird new UI paradigm. I think the implementation risk is low, but the usability risk is high.

Priority: would be nice. Time: 3 days. Risk: low.

## New Create Volume UI

KevinSch has designed a new UI for volume creation in windisk. This dialog replaces the dialogs for the existing “Create”, “Create Volume Set...”, “Create Stripe Set...”, and “Create Stripe Set with Parity...” menu items. This dialog has the same min/max size, and choose-a-size components, but it also allows the user to choose a drive letter, a volume label, and a format (where the format can be “none”). Hitting ‘OK’ forces a commit (perhaps with a confirmation dialog), and then invokes format on the new volume.

Problems: (1) all changes must be committed before partition creation can happen and the volume formatted. Is this desirable? (2) the spec’ed dialog box doesn’t show how much storage will be devoted to redundancy information, as is needed by the “Create Stripe Set with Parity...” dialog, but it could be easily modified to do so.

Priority: would be nice. Time: 1 week. Risk: medium.

# The Work Items: Should

## Better DoubleSpace UI

This item is only relevant if DoubleSpace becomes a requirement for Cairo.

Currently, DoubleSpace volumes are indicated by a list of strings of the form "X: DBLSPACE.001", where X: is the drive letter (if mounted), and the name is the host name of the DoubleSpace volume. This list appears in the FAT partition that hosts the volumes. There are several problems with this:

- it is ugly

- the volume name is mostly useless information

- the volume number is easily truncated on the right if there are many volumes

- you can't select DoubleSpace volumes

As a result of the last point, operations on DoubleSpace volumes are performed by selecting the host volume and choosing "Tools->DoubleSpace Volumes...", and selecting the correct "DBLSPACE.001" from a listbox. At this point, you have a DoubleSpace volume selected and can perform mount/dismount.

I'm assuming we'll have full read/write DoubleSpace in Cairo. This means the valid DoubleSpace operations will be mount (and assign a drive letter), dismount, create, and delete.

I suggest the following. DoubleSpace volumes will appear exactly like other volumes in the disks view. They will have their own color/pattern stripe to distinguish them. The file system string will be "DoubleSpace". The size shown will be either the size made available to them on the host drive or that size multiplied by the expected compression ratio (I prefer the former). There will be a drive letter if mounted, or not if not mounted. All DoubleSpace volumes for a FAT volume will be displayed immediately following that FAT volume. Note that we don't allow DoubleSpace volumes on multi-disk (FT) volumes, so there isn't a problem of deciding which disk bar to display on. Because they are their own "block", they will be selectable via the mouse, and will consequently have commands enabled and disabled based on the selection. They will also have a context menu.

- "Create DoubleSpace Volume" will be an operation enabled only on non-FT FAT volumes.

- "Mount" will be available on unmounted volumes

- "Dismount" will be available on mounted volumes

- "Delete" will be available on all DoubleSpace volumes

DoubleSpace volumes will be able to be "chkdsk"ed, "format"ed, have their label changed, etc, because they can be selected.

Priority: Should, Time: 1 week, Risk: low

## Miscellaneous UI enhancements

- when creating Stripe with Parity (SWP) volumes, we should display both the total amount of space and the amount of usable space. For instance, a 4-component SWP of 100MB has only 75MB of usable space, because ¼ is used for parity. The user should be able to choose the 100MB value, and the 75MB number should change correspondingly  based on user input.

- Currently, when you try to create a 5th primary partition on a disk (only 4 are allowed), you get a message that says, “The disk containing one of the free spaces you have chosen is not able to accept any more partitions.” It should at least say which disk!

- If  you are about to create an extended partition (or other partition) that crosses the 1024 cylinder border, windisk should say how big the partition is allowed to be to be legal to DOS. Currently, you would just have to keep guessing until you found the biggest one that doesn’t pop up the annoying message.

Priority: would be nice. Time: 1 week. Risk: low.

## New commands for mirrored sets

Add “Delete”. Currently, you must break a mirror and then delete each component to delete the entire thing.

Add “Regenerate”. When a Stripe Set with Parity is limping along with a missing member, you can select the remaining volume, select additional free space, choose “Regenerate”, and then the FT driver goes about regenerating the parity information. If a mirror has a missing member, you must first break the mirror, then create a new mirror.  “Regenerate” saves a step, and is more logically consistent with the way Stripes with Parity work.

Priority: should. Time: 3 days. Risk: low.

## Volumes view changes: should

- Configurable column set in table view
The set of columns that is displayed in the table view is currently fixed. We should make it configurable: the user should be able to choose which columns, of a set of possibilities, should be displayed. Note that to do this well requires a much better factorization of the code used to generate data for each column. For instance, it would be great to have a table of functions where each function in the table is capable of generating some interesting piece of data about a volume. Then, for each volume, the set of functions called is the set of columns the user has asked for.

Priority: should. Time: 1 week if we don’t do anything about the column order. Risk: low.

- Columns part of the profile
The set of columns and the width of the columns (which is set by the user by mouse action) should be a user profile item.

Priority: should. Time: 1 day. Risk: low.

## Format

- Disallow quick format of FT volumes. Mike Glass want to force a full sector check:  it doesn’t make sense to have lots of fault tolerance support but not detect bad sectors before using the disk. I believe also that he want the fault tolerance driver to initialize redundancy information during format. He would like to disallow it from the command-line as well. However, we can’t disallow it using old versions of format.com.

- Disallow quick format of a volume for OFS if the volume’s existing format is another file system. OFS depends on the bad block list of a disk appearing is a specific OFS format, and doesn’t read the bad block list of FAT, NTFS, etc. Currently, OFS returns a message saying, “Invalid existing format. This disk cannot be QuickFormatted. Proceed with Unconditional Format (Y/N)?”

- Priority: should. Time: 4 days. Risk: low.

- Do we need to support the /A allocation size parameter?  Format.com supports sizes 512, 1024, 2048, 4096. What file systems support what sizes?  The cluster size parameter is not supported in fmifs.dll, which is what windisk uses to format. If we change the Format entrypoint in fmifs.dll, we need to fix all clients. I think File Manager is the only other client. This means adding File Manager to the build, and releasing it, until Cairo (presumably) gets rid of it. We could alternately add another, new entrypoint, “Format2”, with the new parameter, and not modify File Manager. This preserves backward compatibility better, but isn’t as clean. Chicago, which also has a GUI format, doesn’t need to worry about this because they only support FAT, which doesn’t support different specified cluster sizes.

Priority: should. Time: 2 days. Risk: low.

# The Work Items: Would Be Nice

## Controller/disk view

Graphically depict disk controller and disk topology as an alternate view. Thus, display which disks sit on which controllers. This would be a third windisk view.

We could add a third view to windisk to display the disk controllers, and which disks live on which controllers. We could give SCSI IDs, IDE controller address & interrupt, number of cylinders, heads, tracks, firmware, serial number, identifier, etc. Lots of this information is available in the registry under HKEY_LOCAL_MACHINE\HARDWARE\DEVICEMAP. Is the best way to get at it simply grovelling the registry looking for things I know are interesting, or by the addition of API(s) that provide the relevant information in a reasonable format?  For instance, I could simply look for the “AtDisk” and “Scsi” keys, and, given a description of all the possible bits of information that can be stored there, just go find it. We could presumably get really smart and point out performance bottlenecks on overloaded SCSI chains, etc.

This would be a very useful view for administrators.

Priority: would be nice. Time: 2 weeks. Risk: low.

## Advanced FT support

### FTAPI support

The refers to a new API to integrate hardware and software RAID fault tolerance. The work items, as described by Mike Glass:

- Design API  (Done in theory, just needs to be written up.)

- Implement the API. (I would like to do this.)

- Make it available to ISV/IHV as they are beating us up for it.

- Add support for ISV/IHV specific code. (I understand this is done. [windisk extensions])

- Add capability in windisk to display hardware ft configuration if IHV drivers support the device controls that map to the API.

- Add the capability to manipulate hardware configuration given IHV drivers support the API.

- Rewrite software FT use new API. (This doesn't buy us much, but is politically correct.)

I am more excited about this project than any other and I want to be one of the principals in designing/implementing it. I want to do this this summer. I want about 6 months to do my share. I will do everything below Windisk.

Windisk will construct an FT configuration based on user choice, and then invoke the FTAPI to cause the configuration to take effect. Hardware and software FT configuration would hence be exactly the same. This would presumably require much work in windisk:  the current configuration code would be removed in favor of the new code. If we choose to add additional FT configuration support, such as seamless harware FT configuration, the UI would most likely need to change as well. This is obviously a major change to windisk. It would probably occur in conjunction with multilevel FT support

Priority: would be nice. Time: 4 weeks. Risk: high.

### Multilevel FT support

Support layered RAID configurations. The most interesting (though not the only) possibilities are RAID 0&1, and RAID 53 (by RAB (RAID Advisory Board) definition). So, a RAID 0 stripe set where the components are each mirrored sets, or a RAID 0 stripe where the components are RAID 3 arrays. RAID 0&1 could be implemented entirely in software (in which case the NTFT driver needs to be modified to handle such layering), or half & half with the stripe in software and the mirrored components in hardware, or completely in hardware. The RAID 53 could be either half & half, or all in hardware. It couldn’t be all in software, as we don’t (can’t?) support RAID 3 synchronized arrays in software.

The windisk UI would need to be modified to allow specification of this. It is tempting to design a UI to specify a general hierarchy of FT. For instance, we could display volumes and partitions in a File Manager-like tree view, allowing drag and drop of partitions to merge them into a tree of FT sets. However, there are only very few hierarchical arrangements that make sense from the point of view of performance and availability. For instance, a mirror with RAID 0 components has a much better chance of being put out of commission by a second disk failure than a RAID 0 stripe with mirrored components.

If we provide a richer hierarchy of configuration, we must think carefully about how to explain it to administrators. For instance, perhaps we should have an FT wizard that asks a few questions concerning availability, acceptable cost, expected application read vs. write breakdown, and then provides the admin with a list of alternatives which takes into account current hardware, and gives hardware and performance efficiency numbers for some invented cases.

In summary:

- the NTFT driver must be modified to do multi-level software FT

- windisk must be modified to allow specification of the multi-level configuration. This most likely involves a change in the selection and viewing model, and certainly involves a change in how configuration is set.

- the registry format for storing the configuration must be changed. This involves changing diskreg.lib, and clients that use it.

- if the FTAPI is implemented, it must integrate with this work.

Priority: would be nice. Time: 3 weeks. Risk: high.

## OLE Automation

Support invocation and use of windisk via the OLE Automation interfaces. This would involve creating objects in windisk that would be manipulable via the interfaces; everything now is simply internal.

Priority: would be nice. Time: unknown. Risk: high.

## Format, Chkdsk, and Label

Parts of format, and all of chkdsk and label, are implemented in file system extension classes. The code is very similar for all four file systems we support. In fact, my goal is to share as much code as possible. However, going through the extension interface is somewhat awkward. It might make my life a lot easier, and potentially make the operations seem more integrated if I move all the code directly into windisk, instead of putting it in a Cairo class DLL. BobRi’s format and label for Daytona are implemented like this. If we did this, we could eliminate the file system extension interface, under the assumption that we will only work on FAT, HPFS, NTFS, and OFS, and won’t support any other file systems. We can hard-code the differences between them, including:  (1) legal label characters differ, (2) the chkdsk UI will probably be different, due to the different file system structures. We would like to have a simple, uniform %done UI, but that may be impossible (see above). Finally, (3) the allowable parameters to format differ. For instance, not all file systems support /R and /A.

Priority: consider. Time: 1 week to move the code into windisk. Risk: low.

## Miscellaneous: Would Be Nice

- Clean up registry & UI for non-attached disks
Registry information for disks that aren’t attached is saved, but no disk bar is displayed indicating that windisk has knowledge of the disk. In addition, windisk never purges any disk information from the registry---it maintains all knowledge of every disk that has ever been attached to a machine. This is the subject of at least bug ntbug3:11245.

Priority: would be nice. Time: 1 week. Risk: low.

- Better algorithm for volume set space allocation
Creating a non-maximum-size volume set with differently-sized free spaces creates a weird combination of free space for the volume. For instance, choosing free spaces of 10 and 90 MB, and creating a volume of 50 MB (1/2 the total) uses 5 and 45 MB of space from the free spaces, respectively.  This is a simpler algorithm, but leads to weirder distribution of space. In this case, for instance, it could just use 50 MB from the 90 MB free space. One alternative is to sort the free space largest to smallest, and allocate maximal amounts of free space in decreasing order of free space size until the chosen size is reached. This minimizes the # of free spaces used. It doesn’t necessarily maximize parallelism, though. Another alternative is to allocate space equally from all selected free spaces. If that cannot be done because size X divided by number of free spaces N is bigger than the size of the smallest free space, then first allocate equally the size of the smallest free space. Then, take the remaining space to allocate and divide it by N-1, allocating that space to each remaining free space. Do this until all the space is allocated.

Priority: would be nice. Time: 2 days. Risk: low.

## Volumes view changes: would be nice

- Printing the volumes view
We might want to allow the administrator to print the volumes view; after all, it is a good report of existing disk space. Or, if the listview supports it, we simply allow the admin to select the items in the listview, drag it to the desktop as a scrap, and print the scrap using normal Cairo shell mechanisms.

Priority: would be nice. Time: 1 day. Risk: medium.

## Pagefile support

Currently, the user configures pagefiles via the “Virtual Memory” sub-dialog of the “System” applet in the control panel. You can specify any number of pagefiles---one per volume---and specify minimum and maximum sizes for each. The configuration information is stored in the registry under HKEY_LOCAL_MACHINE\SYSTEM\CurrentControlSet\Control\Session Manager\Memory Management, with the key “Paging Files: REG_MULTI_SZ”, where each string is the name/path of the pagefile, and a minimum/maximum size, e.g. “D:\pagefile.sys 25 50”. The main problem is the pagefile is specified with a drive letter. If this drive letter changes, or the partition is deleted, then the information about the pagefiles is wrong. One suggestion is to include support for pagefiles in windisk. Some possibilities:

- Incorporate the “Virtual Memory” page, appropriately modified, into windisk. Partitions with pagefiles would be appropriately noted in the display, e.g. by another color/pattern/etc. If a volume’s drive letter is changed, the corresponding registry information for the pagefile is also changed to reflect the new “name” for the volume. If a volume with a pagefile is deleted, then the pagefile information for that volume is also deleted from the registry. Creating a pagefile would be bringing up a dialog on a volume that allowed you to specify initial and maximum sizes. Windisk might have a summary dialog or a separate view that gives information about all pagefiles.

- Simply notice, on windisk exit, whether or not all volumes specified as having pagefiles actually exist. If, for example, there is supposed to be a pagefile on volume “F:”, but during the windisk session the user deleted “F:”, then when windisk exits it notices this and pops up a confirmation message “A system paging file is specified to exist on volume F:, which no longer exists. You should either remove the pagefile from this volume using the Virtual Memory page of the System applet of the Control Panel, or create a volume with drive letter ‘F:’. Do you still wish to exist Disk Administrator?”

Priority: would be nice. Time: 3 days. Risk: low.

# The Work Items: Won’t do

## Boot sector configuration

Currently, FT configuration is stored in the registry. It has been proposed (by Mike Glass) that this information be stored in the boot sector instead. The main advantage:  on machines with multiple NT installations, the registries don’t need to be synchronized. The problem currently is that if you boot into a second NT installation, the FT configuration specified in that registry is likely to be wrong. This is the origin of the (disgusting) Config->Search menu item, which migrates registry entries. Setup will of course need to read and preserve the current FT configuration when upgrading NT in place.

Priority: no. Time: 2 weeks. Risk: high.

## Volume creation wizard

Configuring RAID systems, especially if the are layered and consist of both hardware and software parts, is difficult. There are trade-offs to be made between acceptable overhead, required size, and performance requirements, among others. A wizard that asked questions about the administrators requirements and designed a RAID configuration based on available resources might be very useful.

Priority: no. Time: depends on design. Risk: medium.

## Minimize disk bars in disks view

On systems with many disks it becomes obtrusive to have so many disk bars. A desire has been vocalized to “minimize”, “iconize”, or otherwise remove from view selected disks, to conserve screen real estate.

Priority: no. Time: depends on design. Risk: medium.

## FAT partition shrinking

A tool has been written that takes FAT partitions and shrinks them, freeing up space in which another partition (presumably, an OFS partition) may be put. We could integrate this tool into windisk.

We could invoke the tool through the extension interface, but those interfaces don’t support extensions which change the partition table structure. Adding such support would be difficult.  Here are two possibilities:

We invent a protocol for passing partition table information through the extension interfaces. Windisk calls an extension, it messes with the data structures (but doesn’t change anything on disk), and when it returns windisk re-initializes its internal structures and display from what gets returned. This preserves the nice “don’t change anything on disk until the end or an explicit commit” semantics.

We could, for extensions that change the partitions on disk, force a commit before invoking the extension, then force a reboot afterward, or else (when reboots have been eliminated) simply reinitialize by re-reading the disk information. This sounds awful and forces early commits.

Priority: no. Time: unknown. Risk: high.

## Concurrent format/chkdsk

It is not clear whether the u*.dll’s are multi-thread safe. If not, we must enforce a rule that only one format or chkdsk be executed at any time. A cool feature would be to have multiple chkdsks or formats running concurrently. For instance, an admin could multi-select all the unformatted, newly created volumes, and invoke a “format” context menu item which spawned a thread for each volume to perform the formatting.

Priority: no. Time: 2 weeks, if the back-end works. Risk: high.