## Sheet1
|  | PRI | time | when | who
Performance
| heap speed | 2 | 3 mo | PR?/V3 | GregF
| reduce code size | 2 | 1 wk | V3 | ChrisWei
| NCEG FP | 2 | 2 mo | V3 | JamesMa
| stdio "seek without flushing" | 3 | 2-3 wk | V3 | SteveSa
| “mapped” mode for fopen | 3 | 1 wk | V3 | SteveSa
| FP performance | 3 | months | V4
| multiple heaps | 4 | month | ?
Standards
| standard exceptions thrown by CRT | 2 | 3 weeks | V3 | SteveSa
| iostream updates | 2 | months | V3/V4 | JamesMa
| string classes | 2 | months | V4
| bitfield classes | 3 | months | V4
| Standard Template Library | 3 | months | V4
| namespaces | 3 | month(s)? | V4
Debug Support
| debug heap | 2 | months | V3 | GregF
| general debug support | 2 | month | V3/V4 | ChrisWei
| source-level debugging | 3 | month | V3?/V4 | ChrisWei
| leak checking | 4 | month | V3/V4 | SteveSa/ChrisWei
| parameter validity checking | 4 | month | V3/V4 | SteveSa/ChrisWei
Miscellanous
| source release |  | 70% | V2 -> | SteveSa
| nmake build |  | 70% | PR -> | SteveSa
| remove limit on # of file handles | 2 | 2-3 wk | PR | SteveSa
| migrate NT CRT fixes | 2 | 1 wk | PR | GregF
| time zone stuff | 2 | 1 mo | PR?/V3 | GregF
| MT locks to be turned off by users | 3 | 1 wk | V3 | ChrisWei
| complete _int64 support | 2 | 2 wk | V3? | GregF/SteveSa
| UNC support | 2 | 2 weeks | V3?
Internal
| merge with Mac tree | 2 | ongoing |  | everyone
| doc/QA review | 4 | ongoing |  | everyone
| internal regression tests | 3 | weeks |  | everyone
| QA sniffs/BVTs | 3 | ongoing |  | everyone