## input
10 |  | This spread sheet lists all the proposed GDI functions the NT Graphics groups
20 |  | have agreed to spec. For each item the spec author and spec completion date
30 |  | is given. As items are finished the date is changed to done. The development
40 |  | plan indicates if the work has been agreed to by the NT Graphics group. A yes
50 |  | value indicates the item is in our development plan.
60
70 |  | Items not appearing in this spread sheet have not been agreed to and are the
80 |  | responsiblity of some other group.
90
100 |  | See KentD for more information.
110
120
130 |  |  | Spec |  |  | In Devlp
140 | Functionality |  | Owner | Date | Order | Plan | Notes
150
160
170 | Paths
180 |  | BeginPath | PaulB | Done | Early
190 |  | EndPath | PaulB | Done | Early
200 |  | StrokePath | PaulB | Done | Early
210 |  | FillPath | PaulB | Done | Early
220 |  | StrokeAndFillPath | PaulB | Done | Early
230 |  | WidenPath | PaulB | Done | Early
240 |  | PathToRegion | PaulB | Done | Early
250 |  | FlattenPath | PaulB | Done | Early
260 |  | SelectClipPath | PaulB | Done | Early
270 |  | QueryPath | PaulB | Done | Early
280
290 | Clipping
300 |  | GetClipRgn | KentD | Done | Medium |  | Undoc call in Win 3.0
310
320 | Drawing tools functions
330 |  | ExtCreatePen | PaulB | Done | Early |  | Styled Widelines
340 |  | SetMiterLimit | PaulB | Done | Early |  | Styled Widelines
350 |  | SetTextBrush | PaulB | Done | Early |  | Brushes for Text
360
370 | BitBlt
380 |  | PgBlt | PatrichH | Done | Early |  | Rotate Blt
390 |  | Masked BitBlt | PatrickH | Done | Early
400 |  | HalfToning | ChuckWh | ??? | Medium
410 |  | Bitmap blending | ??? | ??? | Medium
420
430 | Drawing Functions
440 |  | AngleArc | w-andrew | Done | Medium
450 |  | PolylineTo | w-andrew | Done | Early
460 |  | PolyBezier | w-andrew | Done | Early
470 |  | PolyBezierTo | w-andrew | Done | Early
480
490 | Transforms
500 |  | SetWorldTransform | WendyWu | Done | Early
510 |  | GetWorldTransform | WendyWu | Done | Early
520 |  | ModifyWorldTransform | WendyWu | Done | Early
530
540
550 | MetaFile Addtions
560 |  | Transform and Clip on Metafile playback |  |  | Late |  | Will be done with Metafile work.
570
580 | Correlation
590 |  | SetCorrelationMode | ChuckWh | ??? | Early
600 |  | SetPickRect | ChuckWh | ??? | Early
610
620 | Improved Font Mapping
630 |  | Nathan Font Mapper |  | ??? | Medium
640 |  | Changes to CreateLogFont | GilmanW | summer | Medium
650
660 | Fonts
670 |  | ExtTextOutExt | KirkO | 1991-03-31 | Medium |  | Alternate Glyphs & Ligatures
680 |  | GetKerningPairs | KirkO | 1991-03-31 | Medium |  | Our only support for kerning
690 |  | Font Path | KirkO |  | Late
700
710 | Unicode Support
720 |  | 19 calls for Win 3.1 support | KirkO | 1991-04-15 | Medium
730
740 | Fractional Character Widths
750 |  | 4 calls | KirkO | 1991-03-31 | Medium
760
770 | Path
780 |  | Multiple paths | PaulB | 1991-02-28 | Medium
790
800 | VGA Palette
810 |  | unknown | PatrickH | 1991-01-31 | Late
820
830
840 | Other items under consideration by Program Management:
850 |  | Device Independent Color |  |  | Medium
860 |  | Discardable Bitmaps |  |  | Medium
870 |  | Cancel Metafile drawing |  |  | Medium
880 |  | Cancel Bitmap drawing |  |  | Medium
890 |  | Device Dependent Bitmaps |  |  | Early
900
910 | Other Items Under considerations
920 |  | 16-bit per pel Jazz Driver
930 |  | User Defined Characters
Revision History
|  | 1991-01-25 | KentD | File Created
|  | 1991-01-31 | KentD | Added Priority Column
|  | 1991-02-08 | KentD | Updated Font stuff
|  | 1991-02-19 | KentD | Removed Win 3.1 functionality
|  | 1991-02-19 | KentD | Added Program Management list
|  | 1991-02-19 | KentD | Updated spec dates
|  | 1991-03-01 | KentD | Added Cancel calls
|  | 1991-03-04 | KentD | Add "order" column per MarkCl.
Deleted some program
mangement items