## Sheet1
Owner | Area | Group | Percent Complete | Comments
a-AaronR | Apps Compatibility Management | TAPI |  | Maintain testing schedule and apps lists
a-AaronR | BVT's | TAPI |  | Run twice a week.
a-AaronR | Dialer | TAPI |  | Functionality and UI
a-AaronR | Location Manager | TAPI |  | Functionality and UI
a-AaronR | Setup/File testing | TAPI |  | Ensure installed files are correct ( for TAPI and SDK )
a-AaronR | Upgrade Scenarios | TAPI/Uni |  | Do upgrade/install scenarios as requested
a-AaronR | Apps Compatibility | TAPI/Uni |  | Do apps testing as requested
a-RRohr | Canonical Number Resolution | TAPI
a-RRohr | Dialing Properties | TAPI |  | Functionality and UI
a-RRohr | Dialing Rules for each country | TAPI
a-RRohr | Upgrade Scenarios | TAPI/Uni |  | Do upgrade/install scenarios as requested
a-RRohr | Apps Compatibility | TAPI/Uni |  | Do apps testing as requested
a-SSwan | BVT's | TAPI |  | Run Daily
a-Sswan | Run API tests | TAPI |  | Run as scheduled by API tester. Not responsible for reading logs, or recovering from errors.
a-Sswan | Upgrade Scenarios | TAPI/Uni |  | Do upgrade/install scenarios as requested
a-Sswan | Apps Compatibility | TAPI/Uni |  | Do apps testing as requested
XiaoD | API Testing | TAPI
XiaoD | Upgrade Scenarios | TAPI/Uni |  | Do upgrade/install scenarios as requested
XiaoD | Apps Compatibility | TAPI/Uni |  | Do apps testing as requested
PeterJe | BVT Automation | TAPI
PeterJe | Test plan maintenance | TAPI
PeterJe | Upgrade Scenarios | TAPI/Uni |  | Do upgrade/install scenarios as requested
PeterJe | Apps Compatibility | TAPI/Uni |  | Do apps testing as requested